## Sheet1
Name | Date | Punch In | Punch Out | Description of Work
Connor | 2025-10-10 | 13:00 | 17:00 | Research on vest module options
Nico | 2025-10-14 | 17:00 | 18:00 | Research on sensor options for depth estimation, reaching out to researcher and consultants
Elias | 2025-10-16 | 12:30 | 12:55 | Researching interfacing with the built in iPhone lidar through swift and libraries and reaching out to MIT researchers related to our project
Connor | 2025-10-18 | 1:00 | 1:45 | Ordering parts and Outreach
Nico | 2025-10-24 | 15:00 | 19:00 | Researching and designing vest and soft nodes
Connor | 2025-10-24 | 20:30 | 22:00 | Hardware setup
Elias | 2025-10-24 | 21:00 | 0:00 | Reseraching and test runngin setting up Connection with Pi to iPhone through BLE
Shiner | 2025-10-24 | 22:00 | 0:45 | Researching PI and BLE
Elias | 2025-10-25 | 14:00 | 17:00 | Successfully configure Bluetooth on the Raspberry Pi 5
Shiner | 2025-10-25 | 14:00 | 17:00 | Troubleshooting iPhone and Pi bluetooth connection
Connor | 2025-10-25 | 17:00 | 19:00 | Researching Microcontroller feedback loop
Nico | 2025-10-25 | 17:00 | 19:00 | Designing soft nodes
Elias | 2025-10-25 | 18:00 | 22:00 | Deep Dive into Blue with Raspberry Pi reading documentation from argenox.com attempted some barebones scripts
Connor | 2025-10-26 | 5:00 | 10:00 | Soldering smd components. Microcontroller setup
Nico | 2025-10-26 | 13:00 | 14:00 | Designing and outreach
Shiner | 2025-10-26 | 16:00 | 19:00 | Testing and finishing up the BLE connection
Nico | 2025-10-26 | 17:00 | 23:00 | Cleaning up models and researching materials
Connor | 2025-10-26 | 16:00 | 22:30 | Full setup for a single node and schematic design
Shiner | 2025-10-26 | 19:15 | 21:30 | Confirming iPhone connection to Pi is seamless and efficient and cleaning up
Elias | 2025-10-26 | 14:00 | 18:30 | Finally Fixed WiFi problem with the Pi had to add Wifi Sharing from my laptop through the correct ethernet port updated some code to have correct logging functionality
Elias | 2025-10-26 | 19:15 | 21:30 | Completed the BLE receiver code and successfully demonstrated it
Connor | 2025-11-02 | 10:00 | 12:00 | Tubing set up
Connor | 2025-11-06 | 5:00 | 17:00 | Tubing, breadboarding, and physical prototype skeleton
Shiner | 2025-11-06 | 15:00 | 17:30 | Reviewing BLE connection and researching BLE GATT for Pi to microcontroller setup
Elias | 2025-11-07 | 16:00 | 21:00 | Research and reviewed SPI communication between the Pi and feather microcontroller and created a skeleton code template for storing the JSON payload
Nico | 2025-11-08 | 0:00 | 4:00 | Tubing and pneumatics setup/ math
Shiner | 2025-11-08 | 14:00 | 17:15 | Looked at skeleton code for storing JSON payload and researched how to incorporate it into microcontroller
Nico | 2025-11-09 | 11:00 | 13:00 | Consulting and research
Shiner | 2025-11-10 | 12:00 | 17:30 | Investigated and researched methods for converting LiDAR proximity values into discrete pressure levels based on actuator constraints
Elias | 2025-11-11 | 11:00 | 17:00 | Did in depth review of gRPC - Protobuf in case we needed to have a server for observation alongside our BLE
Shiner | 2025-11-11 | 16:00 | 20:00 | Understanding Rust language and tooling to prepare for receiver implementation
Shiner | 2025-11-11 | 21:00 | 23:30 | Reviewed BLE constraints for transmitting LiDAR grid data and compared JSON vs compact binary formats to prepare for later implementation.
Nico | 2025-11-13 | 14:30 | 18:00 | Redesigning node and research on flat pneumatic actuator
Shiner | 2025-11-13 | 19:00 | 22:00 | Researched JSON deserialization approaches and example 2D array validation techniques in Rust
Nico | 2025-11-14 | 1:00 | 3:00 | Assembly of pneumatics
Elias | 2025-11-14 | 14:00 | 18:00 | Attempted to solve connections issues with the pi and computers which we trying to develope with, bought a new hdmi cable which was incorrect, then finally returned it and bought a micro hdmi cable for the pi and solved all dev issues
Connor | 2025-11-14 | 17:30 | 18:00 | Micro controller code
Shiner | 2025-11-14 | 20:00 | 0:00 | Reviewed microcontroller code and researched the correct 2 value state patterns needed to support four pressure levels per node.
Connor | 2025-11-15 | 12:30 | 19:00 | Lab testing with compressed air and end to end connections
Shiner | 2025-11-15 | 14:00 | 20:00 | Implemented and completed JSON parsing, grid validation, and node state mapping, debugged for a while to fix issue with listening on wrong inferface
Elias | 2025-11-15 | 15:00 | 20:00 | Reseraching SPI protocols and did very extensive debugging to finally discover we were listening on if00 not if01
Nico | 2025-11-15 | 22:00 | 2:00 | Flat Pneumatic casting
Nico | 2025-11-16 | 14:00 | 19:00 | Testing first rounds of pneumatic casts and casting 2nd round
Elias | 2025-11-16 | 15:00 | 20:30 | Attempting to develope a more effeciently threaded Rust file to reduce the latency from the iphone down to the communication chain to the microcontroller

## Colin Hours
Start Date | Start Time | End Date | End Time | Duration (h) | Description
14/11/2025 | 15:00 | 14/11/2025 | 19:00 | 4:00 | Helped test LiDAR application + BLE receiver functionality in tandem with the pressure node system
14/11/2025 | 10:00 | 14/11/2025 | 17:00 | 7:00 | Implemented LiDAR + node grid processing in the iPhone application, fixed BLE transmissions with Raspberry Pi
13/11/2025 | 14:00 | 13/11/2025 | 17:00 | 3:00 | Researched LiDAR implementation methods and helped set up Raspberry Pi in lab
26/10/2025 | 13:00 | 26/10/2025 | 16:00 | 3:00 | Finished BLE transmissions
24/10/2025 | 11:00 | 24/10/2025 | 13:00 | 2:00 | Set up remote connections to Raspberry Pi for debug, set up user accounts for others to access
23/10/2025 | 12:00 | 23/10/2025 | 16:00 | 4:00 | Researched methods for receiving BLE messages, developed prototype receiving for verifying interface
20/10/2025 | 12:00 | 20/10/2025 | 14:30 | 2:30 | Develop initial LiDAR interface with BLE discovery functionality
19/10/2025 | 10:30 | 19/10/2025 | 12:00 | 1:30 | Initialize swift project, documentation reading (Swift UI and CoreBluetooth SDK)
18/10/2025 | 15:00 | 18/10/2025 | 15:30 | 0:30 | Provisioned Raspberry Pi 5 with Raspberry Pi OS Lite, configured and troubleshooted SSH connectivity
18/10/2025 | 11:00 | 18/10/2025 | 14:00 | 3:00 | Formulated problem of projecting LiDAR depth map to an i x j pressure grid, researched ways of extracting LiDAR depth map from iOS app, drafted high-level architecture for system
16/10/2025 | 13:00 | 16/10/2025 | 16:00 | 3:00 | Researched communication methods for iPhone and Raspberry Pi, compared approaches for continuous data streaming and discrete sensor commands from iPhone LiDAR